## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1. Milestone: Tablet Installation | Milestone
1.1 Research tablet vendors. |  | 2023-05-08 | 2023-05-15 | 7 | Peta
1.2 Select tablet vendor |  | 2023-05-15 | 2023-05-16 | 1 | Seydou
1.3 Sign Contract with Vendor |  | 2023-05-16 | 2023-05-19 | 3 | Carmen
1.4 Order Tablets | Ten days from oder date to receiving. | 2023-05-19 | 2023-05-29 | 10 | Alex
1.5 integrate Tablets with POS Software | If POS version is 3.0 or later, this will take a few hours. If not, then it will take 3 days. | 2023-05-29 | 2023-06-01 | 3 | Carmen
2. Milestone: Electrical Power | Milestone
2.1 Find electricians |  | 2023-06-01 | 2023-06-08 | 7 | Carmen
2.2 Get quotes |  | 2023-06-08 | 2023-06-11 | 3 | Seydou
2.3 Sign Contract |  | 2023-06-11 | 2023-06-14 | 3 | Alex
2.4. Schedule Work |  | 2023-06-14 | 2023-06-15 | 1 | Peta
3. Milestone: Website Design | Milestone
3.1 Research vendors |  | 2023-06-15 | 2023-06-22 | 7 | Peta
3.2 Select vendor |  | 2023-06-22 | 2023-06-23 | 1 | Makayla
3.3 Draw up Contracts |  | 2023-06-23 | 2023-06-26 | 3 | Peta
3.4 Determine design |  | 2023-06-26 | 2023-07-10 | 14 | Carmen
3.5 Upload to site |  | 2023-07-10 | 2023-07-11 | 1 | Alex
4. Milestone: Training | Milestone
4.1 Training Prep |  | 2023-07-11 | 2023-07-18 | 7 | Seydou
4.2Hold Staff Meeting to Advise of Project |  | 2023-07-18 | 2023-07-19 | 1 | Peta
4.2 Determine Small Group to be Trained |  | 2023-07-19 | 2023-07-20 | 1 | Seydou
4.3. Train Small Group of Waitstaff |  | 2023-07-20 | 2023-07-23 | 3 | Makayla
4.4 Small Group Trains Rest of Waitstaff |  | 2023-07-23 | 2023-07-25 | 2 | Makayla
5. Milestone: Test | Milestone
5.1 Schedule a Sunday Morning at North Location |  | 2023-07-25 | 2023-07-26 | 1 | Peta
5.2 Invite Friends and Family |  | 2023-07-26 | 2023-07-27 | 1 | Alex
5.3 Provide Customer Satisfaction Surveys |  | 2023-07-27 | 2023-07-28 | 1 | Carmen
5.4 Analyze Results |  | 2023-07-28 | 2023-07-30 | 2 | Seydou
6. Milestone: Modifications (if needed) | Milestone
7. Milestone: Launch | Milestone
Formulas:
Due Date = [Start Date]+[Duration]
Start Date = [Due Date, row above]

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
1. Milestone: Tablet Installation |  | 0
1.1 Research tablet vendors. |  | 7
1.2 Select tablet vendor |  | 0
1.3 Sign Contract with Vendor |  | 3
1.4 Order Tablets |  | 10
2. Milestone: Electrical Power |  | 3 | 4 | 4 | 4 | H
2.1 Find electricians |  | 0
2.2 Get quotes |  | 7
2.3 Sign Contract with Electrician |  | 3
2.3 Schedule Work | Notify GMs when their locations need to close for wiring. Check with electrician on whether mornings or afternoons work better with their schedule. | 3
3. Milestone: Website Design |  | 0
3.1 Research vendors |  | 0
3.2 Select vendor |  | 7
3.3 Draw up Contracts |  | 0
3.4 Determine design |  | 3
3.5 Upload to site |  | 14
4. Milestone: Training |  | 0.5 | 10 | 14 | 21 | M
4.1 Hold Staff Meeting to Advise of Project |  | 1
4.2 Determine Small Group to be Trained |  | 7
4.3. Train Small Group of Waitstaff |  | 1
4.4 Small Group Trains Rest of Waitstaff |  | 1
5. Milestone: Test |  | 0
5.1 Schedule a Sunday Morning at North Location |  | 1
5.2 Invite Friends and Family |  | 1
5.3 Provide Customer Satisfaction Surveys |  | 1
5.4 Analyze Results |  | 2
6. Milestone: Modifications (if needed) |  | 0
7. Milestone: Launch |  | 0

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Retail and Restaurant Tablet POS: Everything You Need to Know | https://www.nccusa.com/retail-and-restaurant-tablet-pos-everything-you-need-to-know/ | 2023-08-31 | Improves operations, increases customer satisfaction, boosts overall revenue. What is the plan to update tablet hardware when the time comes?
7 Vital Steps in a Successful Restaurant Technology Rollout | https://qsrautomations.com/blog/restaurant-technology/7-vital-steps-technology-rollout/ | 2023-08-31 | Identify who will perform training and which employees need training.
Best Uses for Tablets at Your Restaurant | https://www.business.com/articles/best-tablet-uses-restaurants/ | 9-17-2023
How to Launch A Restaurant POS Platform: 4 Simple Steps to Success | https://www.revolutionordering.com/blog/restaurant-pos-platform | 9-17-2023
Best Practices for Your Digital Menu | https://www.barandrestaurant.com/operations/best-practices-your-digital-menu | 9-17-2023

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Average ticket time | the amount of time between placing an order and delivering it to the table | Appetizers or Entrees? | eight minutes for appetizers and 12-15 minutes for entrees | FALSE
Check out time | the time it takes to check out using a credit or debit card at the table | How long did check out take? | one minute or less | FALSE
Technical issues | Any technical issues with the tablet | Did any technical issues occur? | Less than 5% | FALSE
Order Accuracy | percent of orders that were what the customer ordered | Were the items received what the customer ordered | 98% correct | FALSE
Average wait time | Average amount of time customer waits in the lobby to be seated | How long did the customer wait before being seated? | 10 minutes or less | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5